## Sheet1
ID | Phase | Task | Owner | Due Date | Status | Progress % | Notes
1 | A - Framing | Define problem statement and research questions | Team | Late October | Complete | 100 | RSS framework defined
2 | A - Framing | Identify Key Performance Indicators | Team | Late October | Complete | 100 | Usage, service quality, equity metrics
3 | A - Framing | Document project risks and mitigation | Team | Late October | Complete | 100 | Geospatial and GTFS gaps documented
4 | A - Framing | Create comprehensive indicator list | Team | Late October | Complete | 100 | Indicators for RSS finalized
5 | B - Data/Env | Set up GitHub repository structure | Yuchen | Late October | In Progress | 80 | Scaffold created
6 | B - Data/Env | Create requirements.txt/environment.yml | Yuchen | Late October | In Progress | 75 | Core dependencies listed
7 | B - Data/Env | Set up SQLite database | Eric | Early November | Not Started | 0 | Pending pilot data
8 | B - Data/Env | Design database schema for RSS inputs | Eric | Early November | In Progress | 20 | Draft schema in progress
9 | B - Data/Env | Develop minimal ETL pipeline | Eric | Early November | Not Started | 0 | Starts after schema done
10 | B - Data/Env | Create data dictionary | Eric | Early November | Not Started | 0 | Document all fields and sources
11 | B - Data/Env | Ingest MBTA Speed Restrictions data | Eric | Early November | Not Started | 0 | Service quality indicator
12 | B - Data/Env | Ingest MBTA Monthly Ridership data | Eric | Early November | Not Started | 0 | By mode and line
13 | B - Data/Env | Ingest Fall 2024 Rail Ridership by Stop | Eric | Early November | Not Started | 0 | Stop-level granularity
14 | B - Data/Env | Ingest MBTA Travel Times 2024 | Eric | Early November | Not Started | 0 | Performance indicator
15 | B - Data/Env | Ingest 2024 Passenger Survey | Eric | Early November | Not Started | 0 | Qualitative satisfaction
16 | B - Data/Env | Perform data quality checks | Dhanrithii | Early November | Not Started | 0 | Flag missing/unusual values
17 | C - Analytics | Define RSS formula and weights | Yuchen | Mid November | Not Started | 0 | Create weights.yml
18 | C - Analytics | Implement RSS computation system level | Yuchen | Mid November | Not Started | 0 | Overall MBTA score
19 | C - Analytics | Implement RSS computation line level | Yuchen | Mid November | Not Started | 0 | Red, Orange, Blue, Green lines
20 | C - Analytics | Implement RSS computation station level | Yuchen | Mid November | Not Started | 0 | Individual stations
21 | C - Analytics | Conduct sensitivity analysis | Yuchen | Mid November | Not Started | 0 | Vary weights ±20%
22 | C - Analytics | Perform equity gap analysis | Yuchen | Mid-Late November | Not Started | 0 | Demographics by tract
23 | C - Viz | Learn GeoPandas/Folium basics | Dhanrithii | Early November | Not Started | 0 | 1-2 hr spike
24 | C - Viz | Create system-level RSS trend chart | Dhanrithii | Mid November | Not Started | 0 | Time series using Altair
25 | C - Viz | Create line-level comparison chart | Dhanrithii | Mid November | Not Started | 0 | Bar chart by line
26 | C - Viz | Create station heatmap | Dhanrithii | Mid-Late November | Not Started | 0 | Choropleth map
27 | C - Viz | Create factor contribution breakdown | Dhanrithii | Mid-Late November | Not Started | 0 | Stacked bar chart
28 | C - Viz | Create equity gap visualization | Dhanrithii | Mid-Late November | Not Started | 0 | RSS vs demographics
29 | D - Package | Write methodology section | Yuchen | Late November | Not Started | 0 | RSS formula explanation
30 | D - Package | Write results section | Yuchen | Late November | Not Started | 0 | Key findings and charts
31 | D - Package | Compile data documentation | Dhanrithii | Late November | Not Started | 0 | Data dictionary, licenses
32 | D - Package | Finalize presentation slides | Team | Late November | Not Started | 0 | Full presentation deck
33 | D - Package | Update Excel progress tracker | Dhanrithii | Late November | In Progress | 5 | Final updates
34 | D - Package | Practice presentation delivery | Team | Late November | Not Started | 0 | Rehearse 15-20 min presentation
35 | D - Package | Final validation and preparation | Team | Late November | Not Started | 0 | Ready for Dec 1 presentation